## Sheet1
Health Research Charities Ireland (HCRI) - HRB Joint Funding Scheme
Timelines and Deadlines
|  |  | 2019 | [13 empty] | 2020
| Action/Deadlines |  | Sept | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
|  | w/c | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2019-01-06 | 2019-01-13 | 2019-01-20 | 2019-01-27 | 2019-02-03 | 2019-02-10 | 2019-02-17 | 2019-02-24 | 2019-03-02 | 2019-03-09 | 2019-03-16 | 2019-03-23 | 2019-03-30 | Apr: 2019-04-06; May: 2019-05-04
1 | Launch of Call |  | 2019-10-01 | 2019-10-01
2 | Deadline to Submit Lay oriented Information about Research Proposal to Cystinosis CAB Members |  |  |  | 2019-10-18
3 | Meeting to Review of Research Proposals by Cystinosis CAB members - Public Patient Involvement/Engagment (PPI) | [5 empty] | 01-03-Nov
4 | Feedback from Cystinosis CAB to Researchers to feed into Final Proposal | [6 empty] | 2019-11-08
5 | Deadline for Submission of Proposals to Cystinosis Ireland | [8 empty] | 2019-11-18
6 | Cystinosis Peer Review (will include a PPI review)
7 | Submission of Peer Review Conflict of Interest forms by Cystinosis Ireland to HRB for checking | [15 empty] | 2019-01-10
8 | Cystinosis Ireland to forward abstracts of applications to HRB | [19 empty] | 2019-02-07
9 | Collation of Peer Reviews by Cystinosis Ireland
10 | Researcher Right to Reply to Peer Review Comments (researchers allowed 10 days only to respond)
11 | Preparation of Cystinosis Ireland Supporting Documents
12 | Review of Proposals, peer reviews & replies by the Cystinosis Ireland Research Group | [24 empty] | 2019-03-10
13 | Cystinosis Ireland Executive Committee - Final selection of Proposals to support | [25 empty] | 2019-03-19
14 | Submission of Selected Proposals by Cystinosis Ireland and Approved Researchers | [28 empty] | Apr: 2019-04-06
15 | Joint Funding Committee Meeting | [28 empty] | Jun: Early June 2020
16 | HRB Board Meeting | [28 empty] | Jun: June 2020
17 | Applicant Notification | [28 empty] | Jul: July 2020
18 | Contracts Issued | [28 empty] | Sep: Sep/Oct 2020
19 | Research Project Start Date | [28 empty] | Nov: November 2020